## Sheet1
story points | iteration | dates of iteration |  |  | velocity
85 | 0 | Sept - 1/14 |  |  | 12
73 | 1 | 1/15-1/28 |  |  | 12
61 | 2 | 1/29-2/13 |  |  | 17
41 | 3 | 3/8-3/22 | week 1,2 |  | 5 | 11.5
31 | 4 | 3/23 - 4/5 | week 3,4 |  | 19
12 | 5 | 4/6-4/19 | week 5,6 | PROJECTED | 12
0 | 6 | 4/20-5/3 | week 7,8 |  |  | 12.8
May 14th - last day of classes
Sprint 5: (19, more like 13ishs)
8 - Data integration (integrate it)
5 - customize data
3 - sales, select industry in environment (?)
3 - update baseline data
Sprint 6: (12)
2 - remove apps
3 - update app
2 - destroy any demo instance from monitor
3 - view status of all active demos (admin)
2 - find old apps
Requested docs: lessons learned, more detailed essay type thing